## Sheet1
corrective_action_id | vendor_id | corrective_action_type | corrective_action_status | corrective_action_severity | trigger_reason | sla_event_id | fulfillment_event_id | related_ticket_id | assigned_owner | remediation_plan_summary | monitoring_start_date | reassessment_date | recovery_status | escalation_required_flag | corrective_action_closed_flag | notes
CA-1001 | VEND-003 | SLA Recovery | Monitoring | Action Required | Repeated SLA breaches triggered operational review. | SLA-1002 | VF-1002 | INC-100012 | Vendor Management | Vendor required to improve fulfillment response consistency and reduce shipment delays. | 2026-05-24 | 2026-06-07 | Improving | TRUE | FALSE | Vendor escalation activity decreased but monitoring remains active.
CA-1002 | VEND-004 | Fulfillment Stabilization | Escalated Review | Escalated Review | Delayed and partial fulfillment events created operational disruption exposure. | SLA-1006 | VF-1006 | INC-100001 | Supply Chain Operations | Vendor required to stabilize shipment completion reliability and improve communication timelines. | 2026-05-24 | 2026-06-10 | Unresolved | TRUE | FALSE | Repeated delayed shipment activity continues during monitoring period.
CA-1003 | VEND-002 | Operational Recovery | Resolved | Monitoring | Escalation-linked shipment delays required operational remediation review. | SLA-1003 | VF-1003 | INC-100007 | Operational Support | Vendor communication expectations reviewed and escalation procedures clarified. | 2026-05-23 | 2026-05-30 | Stable | FALSE | TRUE | Operational escalation frequency decreased after remediation review.
CA-1004 | VEND-005 | Continuity Risk Review | Monitoring | Monitoring | Backup supplier fulfillment delays increased continuity-sensitive monitoring requirements. | SLA-1004 | VF-1004 |  | Inventory Leadership | Vendor required to improve replenishment timeline transparency during backup supply periods. | 2026-05-24 | 2026-06-14 | Monitoring | FALSE | FALSE | Vendor performance remains under continuity-risk observation.
CA-1005 | VEND-001 | Escalation Reduction | Resolved | Advisory | Minor escalation review initiated following temporary shipment coordination concerns. | SLA-1005 | VF-1005 |  | Vendor Management | Vendor coordination processes reviewed with no additional corrective escalation required. | 2026-05-22 | 2026-05-27 | Stable | FALSE | TRUE | Vendor returned to normal operational monitoring status.