## Sheet1
sla_event_id | vendor_id | shipment_id | fulfillment_event_id | sla_category | sla_target_hours | actual_response_hours | sla_status | sla_breach_flag | escalation_required_flag | operational_impact_level | related_ticket_id | review_date | corrective_action_required_flag | notes
SLA-1001 | VEND-002 | SHIP-1001 | VF-1001 | Delivery SLA | 48 | 48 | Met | FALSE | FALSE | Low |  | 2026-05-23 | FALSE | Routine shipment met expected delivery SLA.
SLA-1002 | VEND-003 | SHIP-1002 | VF-1002 | Fulfillment SLA | 72 | 96 | Breached | TRUE | TRUE | High | INC-100012 | 2026-05-24 | TRUE | Partial delayed fulfillment breached SLA and required escalation review.
SLA-1003 | VEND-002 | SHIP-1003 | VF-1003 | Operational Support SLA | 48 | 48 | Monitoring | FALSE | TRUE | Moderate | INC-100007 | 2026-05-23 | FALSE | Pending shipment remained within monitoring window but required ticket visibility.
SLA-1004 | VEND-005 | SHIP-1004 | VF-1004 | Delivery SLA | 72 | 72 | Monitoring | FALSE | FALSE | Moderate |  | 2026-05-24 | FALSE | Backup supplier shipment remains pending but has not exceeded SLA threshold.
SLA-1005 | VEND-001 | SHIP-1005 | VF-1005 | Delivery SLA | 48 | 48 | Met | FALSE | FALSE | Low |  | 2026-05-22 | FALSE | Preferred vendor shipment met delivery expectations.
SLA-1006 | VEND-004 | SHIP-1006 | VF-1006 | Fulfillment SLA | 48 | 72 | Breached | TRUE | TRUE | High | INC-100001 | 2026-05-24 | TRUE | Delayed partial shipment breached fulfillment SLA and required corrective follow-up.