## Executive Summary
Northstar Health Operations
Operational Inventory Executive Summary
Reporting Perdiod: May 21, 2026
KPI Highlights
• Active shortage events identified across multiple operational locations
• Critical inventory shortages currently impacting operational readiness
• Vendor shipment delays contributing to replenishment instability
• Multiple inventory discrepancies remain under investigation
• Escalation activity remains elevated due to shortage and replenishment pressure
Kep Operational Observations
• Inventory operations currently show stable baseline inventory conditions alongside several elevated operational risk areas requiring continued monitoring.
• Critical shortages affecting procedural and intake-related supplies continue to create elevated operational escalation activity.
• Vendor shipment delays and partial fulfillment events are contributing to replenishment instability across selected locations.
•Inventory reconciliation activity continues to identify operational count variances, receiving discrepancies, and workflow integrity concerns.
Recommend Operation Focus Areas
• Continue monitoring high-severity shortage events
• Prioritize delayed replenishment workflows linked to critical inventory items
• Maintain elevated vendor performance monitoring for delayed shipments
• Continue discrepancy reconciliation and operational inventory validation activities

## PivotTables
Inventory Status Distribution |  | Shortage Severity Distribution |  | Vendor Shipment Performance
Row Labels | Count of location_inventory_id | Row Labels | Count of shortage_id | Row Labels | Count of shipment_id
Critical Low | 2 | Critical | 2 | Delayed | 1
Low Stock | 2 | High | 1 | Partial | 1
Normal | 2 | Low | 1 | Pending | 2
Overstocked | 1 | Moderate | 1 | Received | 2
Stockout | 1 | Grand Total | 5 | Grand Total | 6
Grand Total | 8
Inventory Discrepancy Distribution |  | Escalated Operational Events
Row Labels | Count of discrepancy_id | Row Labels | Count of shortage_id
Count Variance | 1 | FALSE | 2
Damaged Inventory | 1 | TRUE | 3
Missing Inventory | 1 | Grand Total | 5
Receiving Error | 1
System Entry Error | 1
Grand Total | 5

## vendor-shipments
shipment_id | vendor_id | item_id | location_id | ordered_quantity | received_quantity | order_date | expected_delivery_date | actual_delivery_date | delivery_status | fulfillment_accuracy_flag | delay_flag | related_ticket_id
SHIP-1001 | VEND-002 | ITEM-1002 | LOC-RALEIGH-03 | 60 | 60 | 2026-05-21 | 2026-05-23 | 2026-05-23 | Received | TRUE | FALSE
SHIP-1002 | VEND-003 | ITEM-1003 | LOC-DURHAM-07 | 50 | 40 | 2026-05-21 | 2026-05-24 |  | Delayed | FALSE | TRUE | INC-100012
SHIP-1003 | VEND-002 | ITEM-1006 | LOC-WAKEFOREST-11 | 45 |  | 2026-05-21 | 2026-05-23 |  | Pending |  | FALSE | INC-100007
SHIP-1004 | VEND-005 | ITEM-1007 | LOC-CARY-HUB-01 | 40 |  | 2026-05-21 | 2026-05-24 |  | Pending |  | FALSE
SHIP-1005 | VEND-001 | ITEM-1001 | LOC-RALEIGH-03 | 80 | 80 | 2026-05-20 | 2026-05-22 | 2026-05-22 | Received | TRUE | FALSE
SHIP-1006 | VEND-004 | ITEM-1005 | LOC-WAKEFOREST-11 | 50 | 35 | 2026-05-21 | 2026-05-23 | 2026-05-24 | Partial | FALSE | TRUE | INC-100001

## inventory-discrepancies
discrepancy_id | item_id | location_id | expected_quantity | counted_quantity | variance_quantity | discrepancy_type | investigation_status | discovered_date | resolved_date | related_ticket_id
DISC-1001 | ITEM-1003 | LOC-DURHAM-07 | 12 | 8 | -4 | Count Variance | Investigating | 2026-05-21 |  | INC-100012
DISC-1002 | ITEM-1006 | LOC-WAKEFOREST-11 | 15 | 0 | -15 | Missing Inventory | Escalated | 2026-05-21 |  | INC-100007
DISC-1003 | ITEM-1008 | LOC-CARY-HUB-01 | 140 | 160 | 20 | System Entry Error | Resolved | 2026-05-20 | 2026-05-21
DISC-1004 | ITEM-1002 | LOC-RALEIGH-03 | 25 | 18 | -7 | Receiving Error | Open | 2026-05-21 |  | INC-100031
DISC-1005 | ITEM-1005 | LOC-WAKEFOREST-11 | 30 | 22 | -8 | Damaged Inventory | Mitigating | 2026-05-21 |  | INC-100018

## shortage-events
shortage_id | item_id | location_id | shortage_detected_date | shortage_severity | estimated_days_of_stockout | operational_impact | escalation_flag | related_ticket_id | resolution_status
SHORT-1001 | ITEM-1003 | LOC-DURHAM-07 | 2026-05-21 | Critical | 3 | Low syringe inventory creating risk for clinic procedure delays | TRUE | INC-100012 | Open
SHORT-1002 | ITEM-1006 | LOC-WAKEFOREST-11 | 2026-05-21 | High | 2 | Thermometer probe cover stockout impacting patient intake workflows | TRUE | INC-100007 | Mitigating
SHORT-1003 | ITEM-1005 | LOC-WAKEFOREST-11 | 2026-05-21 | Moderate | 1 | Reduced PPE inventory levels requiring temporary redistribution | FALSE |  | Monitoring
SHORT-1004 | ITEM-1007 | LOC-CARY-HUB-01 | 2026-05-21 | Critical | 4 | IV start kit shortage impacting emergency procedural readiness | TRUE | INC-100021 | Escalated
SHORT-1005 | ITEM-1002 | LOC-RALEIGH-03 | 2026-05-21 | Low | 1 | Gauze inventory temporarily below recommended safety threshold | FALSE |  | Resolved

## replenishment-events
replenishment_id | item_id | location_id | replenishment_type | requested_quantity | approved_quantity | request_date | expected_arrival_date | received_date | replenishment_status | vendor_id | related_ticket_id
REPL-1001 | ITEM-1002 | LOC-RALEIGH-03 | Vendor Reorder | 60 | 60 | 2026-05-21 | 2026-05-23 | 2026-05-23 | Received | VEND-002
REPL-1002 | ITEM-1003 | LOC-DURHAM-07 | Vendor Reorder | 50 | 40 | 2026-05-21 | 2026-05-24 |  | Delayed | VEND-003 | INC-100012
REPL-1003 | ITEM-1005 | LOC-WAKEFOREST-11 | Internal Transfer | 50 | 40 | 2026-05-21 | 2026-05-22 | 2026-05-22 | Received |  | INC-100001
REPL-1004 | ITEM-1006 | LOC-WAKEFOREST-11 | Vendor Reorder | 45 | 45 | 2026-05-21 | 2026-05-23 |  | In Transit | VEND-002 | INC-100007
REPL-1005 | ITEM-1007 | LOC-CARY-HUB-01 | Vendor Reorder | 40 | 40 | 2026-05-21 | 2026-05-24 |  | Approved | VEND-005

## location-inventory
location_inventory_id | item_id | location_id | current_stock | reorder_point | target_stock_level | safety_stock_level | stock_status | last_count_date
LOCINV-1001 | ITEM-1001 | LOC-RALEIGH-03 | 42 | 30 | 90 | 20 | Normal | 2026-05-21
LOCINV-1002 | ITEM-1002 | LOC-RALEIGH-03 | 18 | 25 | 75 | 15 | Low Stock | 2026-05-21
LOCINV-1003 | ITEM-1003 | LOC-DURHAM-07 | 8 | 20 | 60 | 10 | Critical Low | 2026-05-21
LOCINV-1004 | ITEM-1004 | LOC-DURHAM-07 | 115 | 40 | 120 | 25 | Normal | 2026-05-21
LOCINV-1005 | ITEM-1005 | LOC-WAKEFOREST-11 | 22 | 35 | 100 | 20 | Low Stock | 2026-05-21
LOCINV-1006 | ITEM-1006 | LOC-WAKEFOREST-11 | 0 | 15 | 45 | 8 | Stockout | 2026-05-21
LOCINV-1007 | ITEM-1007 | LOC-CARY-HUB-01 | 14 | 20 | 50 | 10 | Critical Low | 2026-05-21
LOCINV-1008 | ITEM-1008 | LOC-CARY-HUB-01 | 160 | 50 | 150 | 30 | Overstocked | 2026-05-21

## inventory-items
item_id | item_name | item_category | criticality_level | unit_of_measure | preferred_vendor_id | active_flag
ITEM-1001 | Nitrile Exam Gloves | Clinical Supplies | High | box | VEND-001 | TRUE
ITEM-1002 | Sterile Gauze Pads | Wound Care Supplies | High | pack | VEND-002 | TRUE
ITEM-1003 | Syringe 5mL | Clinical Supplies | Critical | case | VEND-003 | TRUE
ITEM-1004 | Alcohol Prep Pads | Clinical Supplies | Moderate | box | VEND-001 | TRUE
ITEM-1005 | Surgical Masks | PPE | High | box | VEND-004 | TRUE
ITEM-1006 | Thermometer Probe Covers | Clinical Supplies | Moderate | box | VEND-002 | TRUE
ITEM-1007 | IV Start Kits | Procedure Supplies | Critical | kit | VEND-005 | TRUE
ITEM-1008 | Biohazard Disposal Bags | Compliance Supplies | High | case | VEND-006 | TRUE